## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understand the problem statement given by the mentor and decide that our project will be a healthcare operations dashboard. | MUST HAVE | Mentor briefing | Samuel Manoj Pinipe | 3- Completed
S1 | S1 | US-002 | Collect KPI ideas for the healthcare domain and group them, instead of putting everything on a single crowded page. | MUST HAVE | US-001 | Samuel Manoj Pinipe | 3- Completed
S2 | S2 | US-003 | Decide the dataset for the project, with more than ten thousand records, after comparing ready datasets with a generated one. | MUST HAVE | US-002 | Samuel Manoj Pinipe | 3- Completed
S2 | S2 | US-004 | Prepare the first PPT explaining the dashboard idea and show it to the mentor for approval. | SHOULD HAVE | US-003 | Samuel Manoj Pinipe | 3- Completed
S3 | S3 | US-005 | Arrange the health programme data in one fact table and four dimension tables so that the same data can be used for all charts. | MUST HAVE | US-003 | Samuel Manoj Pinipe | 3- Completed
S3 | S3 | US-006 | Change our topic to public health surveillance after mentor feedback, because the earlier idea was similar to another group. | MUST HAVE | US-004 | Samuel Manoj Pinipe | 3- Completed
S3 | S3 | US-007 | Write down which dashboard page I will build and which questions my page has to answer. | MUST HAVE | US-006 | Samuel Manoj Pinipe | 3- Completed
S4 | S4 | US-008 | Check every column of the raw files for blanks, wrong data types and strange values before starting the cleaning work. | MUST HAVE | US-005 | Samuel Manoj Pinipe | 3- Completed
S4 | S4 | US-009 | Clean my datasets by removing duplicate rows, negative counts and text entries in number columns, and save the cleaned files. | MUST HAVE | US-008 | Samuel Manoj Pinipe | 3- Completed
S5 | S5 | US-010 | Do EDA on programme coverage, screening numbers and vulnerability, so that I can pick the right KPIs for my dashboard. | MUST HAVE | US-009 | Samuel Manoj Pinipe | 3- Completed
S5 | S5 | US-011 | Create my GitHub repository and keep the data, code and document folders in a proper structure. | SHOULD HAVE | US-009 | Samuel Manoj Pinipe | 3- Completed
S5 | S5 | US-012 | Learn the basic Streamlit page structure by building a small sample app before starting the real dashboard. | SHOULD HAVE | Streamlit practice | Samuel Manoj Pinipe | 3- Completed
S6 | S6 | US-013 | Show eight KPI cards on top of my page covering coverage, screening, beneficiaries, immunisation, high risk people and the vulnerability index. | MUST HAVE | US-010 | Samuel Manoj Pinipe | 3- Completed
S6 | S6 | US-014 | Give State, Year, Month and Programme filters in the sidebar and make sure every KPI and chart changes with them. | MUST HAVE | US-013 | Samuel Manoj Pinipe | 3- Completed
S6 | S6 | US-015 | Build the six charts of my page so the user can see coverage trend, screening versus beneficiaries, age groups, high risk states and vulnerability. | MUST HAVE | US-013 | Samuel Manoj Pinipe | 3- Completed
S6 | S6 | US-016 | Show very big numbers in short form like K, M and B, because the full number was getting cut inside the KPI card. | SHOULD HAVE | US-013 | Samuel Manoj Pinipe | 3- Completed
S6 | S6 | US-017 | Complete my Health Programs and Population Vulnerability dashboard and upload it on 16 August. | MUST HAVE | US-015 | Samuel Manoj Pinipe | 3- Completed
S7 | S7 | US-018 | Write the README so anyone can understand my data model, KPI meanings, cleaning steps and the limitations I found. | MUST HAVE | US-017 | Samuel Manoj Pinipe | 3- Completed
S7 | S7 | US-019 | Test my dashboard properly and note down every mistake I found and how I corrected it. | MUST HAVE | US-017 | Samuel Manoj Pinipe | 3- Completed
S7 | S7 | US-020 | Keep my own repository ready with the project files and my three filled artifact files, as the mentor confirmed individual submission. | MUST HAVE | US-018 | Samuel Manoj Pinipe | 3- Completed
S7 | S7 | US-021 | Practise my dashboard explanation within the given time so I can present it clearly in the final review. | SHOULD HAVE | US-017 | Samuel Manoj Pinipe | 2- In Progress
S8 | S8 | US-022 | Attend the remaining mentor discussions and the final evaluation, and close any change asked during the review. | MUST HAVE | US-020 | Samuel Manoj Pinipe | 1- Not Started
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 193 | 28 | 31 | 37 | 35 | 16 | 16 | 14 | 0 | 0 | 0 | 4 | 4 | 5 | 3
S1 BACKLOG (02-Jul-2026 to 08-Jul-2026)
US-001 | TASK-001 | Attend the first mentor session and note down what is expected in the project. | 02-Jul-2026 | 03-Jul-2026 | Samuel Manoj Pinipe | Requirement Study | Completed | 4 | Day 1: 2; Day 2: 2
US-001 | TASK-002 | Read the problem statement again and list the healthcare areas we can cover. | 03-Jul-2026 | 04-Jul-2026 | Samuel Manoj Pinipe | Requirement Study | Completed | 4 | Day 2: 2; Day 3: 2
US-002 | TASK-003 | Collect KPI ideas for hospital, laboratory and public health areas and note them in one place. | 05-Jul-2026 | 07-Jul-2026 | Samuel Manoj Pinipe | Requirement Discussion | Completed | 6 | Day 4: 2; Day 5: 2; Day 6: 2
US-002 | TASK-004 | Group the KPI ideas into separate dashboard pages instead of one single page. | 07-Jul-2026 | 08-Jul-2026 | Samuel Manoj Pinipe | Scope Planning | Completed | 4 | Day 6: 2; Day 7: 2
S2 BACKLOG (09-Jul-2026 to 15-Jul-2026)
US-003 | TASK-001 | Search for ready healthcare datasets and check how many records and columns they have. | 09-Jul-2026 | 10-Jul-2026 | Samuel Manoj Pinipe | Dataset Planning | Completed | 5 | Day 1: 3; Day 2: 2
US-003 | TASK-002 | Compare a ready dataset with a generated one and decide which one suits our dashboard. | 11-Jul-2026 | 12-Jul-2026 | Samuel Manoj Pinipe | Dataset Planning | Completed | 5 | Day 3: 3; Day 4: 2
US-004 | TASK-003 | Prepare the first PPT with the dashboard idea and the questions each page will answer. | 13-Jul-2026 | 14-Jul-2026 | Samuel Manoj Pinipe | PPT Preparation | Completed | 6 | Day 5: 3; Day 6: 3
US-004 | TASK-004 | Show the PPT to the mentor and write down the corrections she asked for. | 15-Jul-2026 | 15-Jul-2026 | Samuel Manoj Pinipe | Mentor Review | Completed | 3 | Day 7: 3
S3 BACKLOG (16-Jul-2026 to 22-Jul-2026)
US-005 | TASK-001 | Arrange the health programme data into one fact table and four dimension tables. | 16-Jul-2026 | 17-Jul-2026 | Samuel Manoj Pinipe | Data Modelling | Completed | 6 | Day 1: 3; Day 2: 3
US-006 | TASK-002 | Change the topic to public health surveillance after the mentor said our idea was similar to another group. | 18-Jul-2026 | 19-Jul-2026 | Samuel Manoj Pinipe | Scope Refinement | Completed | 5 | Day 3: 3; Day 4: 2
US-007 | TASK-003 | Decide my page as Health Programs and Population Vulnerability and list its questions. | 20-Jul-2026 | 21-Jul-2026 | Samuel Manoj Pinipe | Design | Completed | 5 | Day 5: 3; Day 6: 2
US-007 | TASK-004 | Write down the cleaning steps I will need, like duplicates, blanks and wrong data types. | 22-Jul-2026 | 22-Jul-2026 | Samuel Manoj Pinipe | Planning | Completed | 4 | Day 7: 4
S4 BACKLOG (23-Jul-2026 to 05-Aug-2026)
US-008 | TASK-001 | Check each column for null percentage, data type and minimum maximum values. | 23-Jul-2026 | 25-Jul-2026 | Samuel Manoj Pinipe | Data Profiling | Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2
US-008 | TASK-002 | Note the columns where the data dictionary name and the actual file name are different. | 27-Jul-2026 | 28-Jul-2026 | Samuel Manoj Pinipe | Data Profiling | Completed | 4 | Day 5: 2; Day 6: 2
US-009 | TASK-003 | Write the cleaning code to drop duplicate fact rows and remove negative counts. | 02-Aug-2026 | 03-Aug-2026 | Samuel Manoj Pinipe | Data Cleaning | Completed | 8 | Day 11: 4; Day 12: 4
US-009 | TASK-004 | Remove repeated ids from the dimension files so the join does not increase the row count. | 04-Aug-2026 | 04-Aug-2026 | Samuel Manoj Pinipe | Data Cleaning | Completed | 5 | Day 13: 5
US-009 | TASK-005 | Save the cleaned files and keep the cleaning code along with them. | 05-Aug-2026 | 05-Aug-2026 | Samuel Manoj Pinipe | Data Cleaning | Completed | 3 | Day 14: 3
S5 BACKLOG (06-Aug-2026 to 12-Aug-2026)
US-010 | TASK-001 | Do EDA on programme coverage, people screened and beneficiaries reached. | 06-Aug-2026 | 07-Aug-2026 | Samuel Manoj Pinipe | EDA | Completed | 8 | Day 1: 4; Day 2: 4
US-010 | TASK-002 | Study the population and vulnerability columns and decide my final KPI list. | 08-Aug-2026 | 09-Aug-2026 | Samuel Manoj Pinipe | EDA | Completed | 7 | Day 3: 4; Day 4: 3
US-011 | TASK-003 | Create my GitHub repository with folders for data, dashboards, code and documents. | 10-Aug-2026 | 10-Aug-2026 | Samuel Manoj Pinipe | Repository Setup | Completed | 4 | Day 5: 4
US-012 | TASK-004 | Build a small Streamlit sample app to understand pages, sidebar and charts. | 11-Aug-2026 | 12-Aug-2026 | Samuel Manoj Pinipe | Streamlit Practice | Completed | 6 | Day 6: 3; Day 7: 3
S6 BACKLOG (13-Aug-2026 to 19-Aug-2026)
US-013 | TASK-001 | Write the KPI code for all eight measures and use average for the percentage and index columns. | 13-Aug-2026 | 13-Aug-2026 | Samuel Manoj Pinipe | Development | Completed | 7 | Day 1: 7
US-014 | TASK-002 | Build the State, Year, Month and Programme filters and connect them to every chart. | 14-Aug-2026 | 14-Aug-2026 | Samuel Manoj Pinipe | Development | Completed | 6 | Day 2: 6
US-015 | TASK-003 | Build the coverage trend line chart and the screened versus beneficiaries bar chart. | 15-Aug-2026 | 15-Aug-2026 | Samuel Manoj Pinipe | Visualization | Completed | 7 | Day 3: 7
US-015 | TASK-004 | Build the age group chart, the high risk treemap and the vulnerability bar chart. | 15-Aug-2026 | 16-Aug-2026 | Samuel Manoj Pinipe | Visualization | Completed | 8 | Day 3: 4; Day 4: 4
US-015 | TASK-005 | Build the bubble chart between socioeconomic score and vulnerability and show the correlation value. | 16-Aug-2026 | 16-Aug-2026 | Samuel Manoj Pinipe | Visualization | Completed | 5 | Day 4: 5
US-016 | TASK-006 | Add the short form number display and show the exact value below each KPI card. | 16-Aug-2026 | 16-Aug-2026 | Samuel Manoj Pinipe | Development | Completed | 4 | Day 4: 4
US-017 | TASK-007 | Complete the dashboard and upload my Dashboard 5 files on 16 August. | 16-Aug-2026 | 16-Aug-2026 | Samuel Manoj Pinipe | Upload | Completed | 4 | Day 4: 4
S7 BACKLOG (20-Aug-2026 to 26-Aug-2026)
US-018 | TASK-001 | Write the README with data model, KPI meanings, cleaning steps and limitations. | 20-Aug-2026 | 21-Aug-2026 | Samuel Manoj Pinipe | Documentation | Completed | 6 | Day 1: 3; Day 2: 3
US-019 | TASK-002 | Test data loading, cleaning, KPIs, filters and all six charts one by one. | 21-Aug-2026 | 22-Aug-2026 | Samuel Manoj Pinipe | Unit Testing | Completed | 8 | Day 2: 4; Day 3: 4
US-019 | TASK-003 | Correct the mistakes found in testing and write the action taken for each one. | 22-Aug-2026 | 22-Aug-2026 | Samuel Manoj Pinipe | Defect Fix | Completed | 6 | Day 3: 6
US-020 | TASK-004 | Fill the Agile, Unit Test Plan and Defect Tracker files for my own work. | 23-Aug-2026 | 23-Aug-2026 | Samuel Manoj Pinipe | Documentation | Completed | 5 | Day 4: 5
US-020 | TASK-005 | Upload the project files and the three artifact files to my own repository and send the link. | 23-Aug-2026 | 23-Aug-2026 | Samuel Manoj Pinipe | Submission | Completed | 4 | Day 4: 4
US-021 | TASK-006 | Practise explaining my dashboard within the given time and prepare answers for questions. | 24-Aug-2026 | 26-Aug-2026 | Samuel Manoj Pinipe | Demo Preparation | Not Started | 6 | Day 5: 2; Day 6: 2; Day 7: 2
S8 BACKLOG (27-Aug-2026 to 29-Aug-2026)
US-022 | TASK-001 | Attend the remaining mentor discussion sessions and note any change asked in my page. | 27-Aug-2026 | 27-Aug-2026 | Samuel Manoj Pinipe | Mentor Review | Not Started | 4 | Day 1: 4
US-022 | TASK-002 | Do the final corrections and attend the final evaluation on the last day. | 28-Aug-2026 | 29-Aug-2026 | Samuel Manoj Pinipe | Final Review | Not Started | 5 | Day 2: 3; Day 3: 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | I was not clear how big the project scope should be and how many pages we need. | Listed all KPI ideas first and grouped them into separate pages after discussing with the team.
S2 | Day 3 | I could not decide between a ready dataset and a generated one. | Compared both on record count and columns needed for my charts, then finalised the dataset.
S3 | Day 4 | Our first idea was close to another group's idea. | Mentor suggested public health surveillance, so I changed my page to health programmes and vulnerability.
S4 | Day 3 | Column names in the data file were not the same as the names in the data dictionary. | Wrote the correct mapping in my loading code and noted it in the README.
S4 | Day 11 | After joining the tables my row count became more than the original fact table. | Found repeated ids in the dimension files and removed them before the join.
S5 | Day 2 | The dashboard was becoming slow because the files were loading again for every filter click. | Used caching so the cleaned data loads only once.
S5 | Day 5 | My files were scattered and it was difficult to find the cleaning code. | Made proper folders for data, dashboards, code and documents in my repository.
S6 | Day 1 | Coverage percentage was coming above 100 in the KPI card. | Understood that percentage cannot be added, changed it to average and checked the other rate columns also.
S6 | Day 3 | Population numbers were looking around six times higher than the real value. | Population repeats for all six programmes, so I took it from a duplicate free table.
S6 | Day 4 | Big numbers were getting cut inside the KPI card. | Displayed them in short form and kept the exact number below the card.
S7 | Day 2 | Some filter combinations were showing empty charts without any message. | Added a message that tells the user no data is available for that selection.
S7 | Day 3 | Immunisation count was more than the child population for the same state and month. | Checked my code and found it correct, so I noted it as a data limitation in the README.
S7 | Day 6 | I was not sure how much time I will get for the final demo. | Practised the explanation in short and kept the main KPIs and insights ready first.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 02-Jul-2026 | 08-Jul-2026 | Samuel Manoj Pinipe | Note down every idea during the mentor session itself. | Trying to put all KPIs in one single page. | Discussing with team members before fixing the scope. | Dashboard was divided into separate pages and my page was decided.
2 | S2 | 09-Jul-2026 | 15-Jul-2026 | Samuel Manoj Pinipe | Check the columns of a dataset, not only the number of records. | Selecting a dataset only because it is easily available. | Showing the PPT to the mentor before starting the work. | Dataset was finalised and the first PPT was reviewed.
3 | S3 | 16-Jul-2026 | 22-Jul-2026 | Samuel Manoj Pinipe | Compare our idea with other groups early to keep it different. | Starting charts before understanding the table structure. | Writing the cleaning steps as a plan before coding. | Topic changed to public health surveillance and my page was fixed.
4 | S4 | 23-Jul-2026 | 05-Aug-2026 | Samuel Manoj Pinipe | Check duplicates and repeated ids before joining any tables. | Believing that the data dictionary matches the actual file. | Writing down how many rows are removed in each cleaning step. | Cleaning was completed and the cleaned files were saved with the code.
5 | S5 | 06-Aug-2026 | 12-Aug-2026 | Samuel Manoj Pinipe | Decide the KPIs from EDA results instead of guessing. | Keeping project files without a proper folder structure. | Practising Streamlit with a small app before the main work. | EDA was completed and the repository structure was created.
6 | S6 | 13-Aug-2026 | 19-Aug-2026 | Samuel Manoj Pinipe | Verify each KPI with a small manual calculation. | Adding every column, because percentage and repeated columns are different. | Keeping the KPI code in one file instead of repeating it in charts. | Dashboard was completed and uploaded on 16 August with 8 KPIs and 6 charts.
7 | S7 | 20-Aug-2026 | 26-Aug-2026 | Samuel Manoj Pinipe | Compare a big total with a real limit like population before believing it. | Leaving documentation and testing for the last day. | Noting every limitation as soon as I find it. | Testing was done, defects were closed and the artifact files were filled.
8 | S8 | 27-Aug-2026 | 29-Aug-2026 | Samuel Manoj Pinipe | Practise the demo with time limit before the final review. | Explaining every chart in detail when time is short. | Keeping the repository updated after every change. | Final review preparation is going on.