## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Samuel Manoj Pinipe | 03-Aug-2026 | After joining the fact table with the dimension tables, the row count became more than the original fact table, so all totals were wrong. | S4 | Samuel Manoj Pinipe | Logical | Found repeated ids in the dimension files and removed them before doing the join. | 03-Aug-2026 | Closed | Row count now matches the cleaned fact table.
2 | Samuel Manoj Pinipe | 02-Aug-2026 | Same rows were present twice in the raw fact file, so every total was counted double for those rows. | S4 | Samuel Manoj Pinipe | Logical | Removed duplicate rows as the first cleaning step and noted how many rows were removed. | 02-Aug-2026 | Closed | 96 rows removed out of 6,981.
3 | Samuel Manoj Pinipe | 03-Aug-2026 | Negative values were coming in the high risk individuals column, which is not possible for a count. | S4 | Samuel Manoj Pinipe | Logical | Removed the rows having negative counts and mentioned this in the cleaning notes. | 03-Aug-2026 | Closed | Applied for all count columns, not only high risk.
4 | Samuel Manoj Pinipe | 04-Aug-2026 | Text and blank values in number columns were giving an error while building the charts. | S4 | Samuel Manoj Pinipe | Logical | Converted those columns to numeric so wrong entries become blank instead of stopping the code. | 04-Aug-2026 | Closed | Charts now skip the missing values.
5 | Samuel Manoj Pinipe | 10-Aug-2026 | Dashboard was slow because the CSV files were loading again for every filter change. | S5 | Samuel Manoj Pinipe | Others | Added caching so the cleaned data loads only once in a session. | 10-Aug-2026 | Closed | Filter change response is fast now.
6 | Samuel Manoj Pinipe | 13-Aug-2026 | Program coverage KPI was showing more than 100 percent. | S6 | Samuel Manoj Pinipe | Logical | Understood that percentage cannot be added, changed it to average and checked the other rate columns also. | 13-Aug-2026 | Closed | Vulnerability index was corrected in the same way.
7 | Samuel Manoj Pinipe | 14-Aug-2026 | Big KPI values were getting cut inside the card because the number was too long. | S6 | Samuel Manoj Pinipe | User Interface | Displayed the value in short form like K, M and B and kept the exact number below the card. | 14-Aug-2026 | Closed | Exact value also comes on hover.
8 | Samuel Manoj Pinipe | 15-Aug-2026 | Month names on the coverage chart were coming in alphabetical order starting from April. | S6 | Samuel Manoj Pinipe | User Interface | Set the month column in calendar order so the chart shows January to December. | 15-Aug-2026 | Closed | Checked for all three years in the data.
9 | Samuel Manoj Pinipe | 15-Aug-2026 | Coverage chart was showing one single line for three years, so the yearly pattern was not visible. | S6 | Samuel Manoj Pinipe | User Interface | Separated the line year wise on the same month axis. | 15-Aug-2026 | Closed | Year comparison is clear now.
10 | Samuel Manoj Pinipe | 15-Aug-2026 | Children, adult and elderly numbers were around six times more than the actual population. | S6 | Samuel Manoj Pinipe | Logical | Population repeats for all six programmes, so I took it from a duplicate free table and used average. | 16-Aug-2026 | Closed | Only population columns are like this, other columns are still added.
11 | Samuel Manoj Pinipe | 16-Aug-2026 | Treemap total was not matching with the high risk individuals KPI value. | S6 | Samuel Manoj Pinipe | Logical | Used the same filtered data for the treemap that the KPI is using. | 16-Aug-2026 | Closed | Both values match now for every filter.
12 | Samuel Manoj Pinipe | 16-Aug-2026 | Child immunisation count is more than the child population for the same state and month. | S6 | Samuel Manoj Pinipe | Others | Checked my calculation and found it correct, so I raised it as a data problem instead of changing the value. | 21-Aug-2026 | Open | Written as a known limitation in the README; value should be confirmed before using it.
13 | Samuel Manoj Pinipe | 16-Aug-2026 | The source filter I planned could not be built because the fact table has no source id column. | S6 | Samuel Manoj Pinipe | Standards | Confirmed there is no joining key and removed that filter from the scope. | 16-Aug-2026 | Closed | Mentioned as a limitation in the README.
14 | Samuel Manoj Pinipe | 21-Aug-2026 | When a filter combination had no data, empty charts were showing without any message. | S7 | Samuel Manoj Pinipe | User Interface | Added a message telling the user that no data is available for that selection. | 21-Aug-2026 | Closed | Message also tells which selection gave no data.
15 | Samuel Manoj Pinipe | 22-Aug-2026 | Same styling code was repeated in different chart files, so the pages were not looking uniform. | S7 | Samuel Manoj Pinipe | Maintainability | Moved the theme colours and styling into one common file used by all pages. | 22-Aug-2026 | Closed | New pages now take the theme automatically.
16 | Samuel Manoj Pinipe | 22-Aug-2026 | I planned an India map for the vulnerability visual but delivered a bar chart. | S7 | Samuel Manoj Pinipe | Others | Map needs a boundary file which is not given with the dataset, so I used a ranked bar chart instead. | 22-Aug-2026 | Open | Can be done later if the boundary file is provided.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others